## Project Planner
Project Title
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74
| 1.1 Project Background & Overview: | 1 | 2 | 1 | 1 | 0%
| 1.2 Dataset Analysis & Selection | 3 | 3 | 2 | 1 | 0%
| 1.3 Project Scope Definition | 6 | 2 | 3 | 2 | 0%
| 1.4 Project Milestone Setting | 8 | 1 | 5 | 1 | 0%
| 2.1 Use Case Definition | 9 | 2 | 6 | 2 | 0%
| 2.2 Use Case In-depth Analysis | 11 | 3 | 8 | 3 | 0%
| 2.3 User Interaction Requirement Analysis | 14 | 2 | 11 | 3 | 0%
| 2.4 Functional Module Division | 16 | 2 | 14 | 2 | 0%
| 2.5 Prototype & Interface Sketch Design | 18 | 3 | 16 | 2 | 0%
| 2.6 Data Structure & Flowchart Design | 21 | 3 | 18 | 2 | 0%
| 2.7 UML Modeling & Design | 24 | 4 | 20 | 4 | 0%
| 3.1 Data Preprocessing & Cleaning | 28 | 4 |  |  | 0%
| 3.2 Class & Component Implementation | 32 | 5 |  |  | 0%
| 3.3 Algorithm Design & Optimization | 37 | 5 |  |  | 0%
| 3.4 User Interface Development | 42 | 4 |  |  | 0%
| 3.5 API & Method Implementation | 46 | 4 |  |  | 0%
| 3.6 Software Packaging & Test Preparation | 50 | 2 |  |  | 0%
| 4.1 Test Plan Design | 52 | 3 |  |  | 0%
| 4.2 Internal Testing & Verification | 55 | 5 |  |  | 0%
| 4.3 Test Result Analysis | 60 | 2 |  |  | 0%
| 4.4 Issue Fixing & Optimization | 62 | 4 |  |  | 0%
| 4.5 Final Software Packaging & Delivery | 66 | 2 |  |  | 0%
| 5.1 Project Documentation Writing | 68 | 4 |  |  | 0%
| 5.2 Project Review & Summary | 72 | 2 |  |  | 0%
Activity 33 |  |  | 2 |  | 0%