## Sheet1
RACI Chart | Person
Activity | Chein Huang | Siqi Wu | Zhanrui Liao
1.1 Project Background & Overview: | I | C | A | R = Responsible; A = Accountable; C = Consult; I = Inform
1.2 Dataset Analysis & Selection | I | C | A
1.3 Project Scope Definition | I | C | A
1.4 Project Milestone Setting | I | C | A
2.1 Use Case Definition | A | C | I
2.2 Use Case In-depth Analysis | A | C | I
2.3 User Interaction Requirement Analysis | A | C | I
2.4 Functional Module Division | A | C | I
2.5 Prototype & Interface Sketch Design | A | C | I
2.6 Data Structure & Flowchart Design | A | C | I
2.7 UML Modeling & Design | A | C | I
3.1 Data Preprocessing & Cleaning | R | A | R
3.2 Class & Component Implementation | R | A | R
3.3 Algorithm Design & Optimization | R | A | R
3.4 User Interface Development | R | A | R
3.5 API & Method Implementation | R | A | R
3.6 Software Packaging & Test Preparation | R | A | R
4.1 Test Plan Design | R | C | A
4.2 Internal Testing & Verification | R | C | A
4.3 Test Result Analysis | R | C | A
4.4 Issue Fixing & Optimization | R | C | A
4.5 Final Software Packaging & Delivery | R | C | A
5.1 Project Documentation Writing | A | I | R
5.2 Project Review & Summary | A | I | R