## Sheet1
stage | task | details | estimation
sprint1-1.0 Project Initiation | 1.1 Project Background & Overview: | Define the objectives, background, and expected outcomes of the project. | 2 days
| 1.2 Dataset Analysis & Selection | Analyze various datasets and select the most suitable one for further analysis. | 3 days
| 1.3 Project Scope Definition | Clearly define the scope of the project and the expected deliverables. | 2 days
| 1.4 Project Milestone Setting | Set key project milestones and their expected completion dates. | 1 days
sprint2-2.0 System Design & Planning | 2.1 Use Case Definition | Define the main use cases based on user requirements | 2 days
| 2.2 Use Case In-depth Analysis | Conduct a detailed analysis of each use case | 3 days
| 2.3 User Interaction Requirement Analysis | Analyze how users will interact with the system and define the main user interfaces and interaction methods | 2 days
| 2.4 Functional Module Division | Divide the software into different functional modules based on system requirements. | 2 days
| 2.5 Prototype & Interface Sketch Design | Design preliminary prototypes and interface sketches for the software | 3 days
| 2.6 Data Structure & Flowchart Design | Design the main data structures and software flowcharts | 3 days
| 2.7 UML Modeling & Design | Use UML to model the system, including class diagrams, sequence diagrams, etc. | 4 days
sprint3-3.0 Software Development & Implementation | 3.1 Data Preprocessing & Cleaning | Preprocess and clean the dataset to ensure data quality. | 4 days
| 3.2 Class & Component Implementation | Implement the main classes and components based on UML designs | 5 days
| 3.3 Algorithm Design & Optimization | Algorithm Design & Optimization | 5 days
| 3.4 User Interface Development | Develop the user interface ensuring it's user-friendly | 4 days
| 3.5 API & Method Implementation | Design and implement the main APIs and methods. | 4 days
| 3.6 Software Packaging & Test Preparation | Package the software and prepare for testing. | 2 days
sprint4-4.0 Software Testing & Delivery | 4.1 Test Plan Design | Design a detailed software testing plan. | 3 days
| 4.2 Internal Testing & Verification | Conduct internal software testing and verification. | 5 days
| 4.3 Test Result Analysis | Analyze the test results and identify software issues and defects. | 2 days
| 4.4 Issue Fixing & Optimization | Fix issues based on test results and optimize the software | 4 days
| 4.5 Final Software Packaging & Delivery | Package the software and deliver it to the customer | 2 days
sprint5-5.0 Version Control & Documentation | 5.1 Project Documentation Writing | Write detailed project documentation, including design documents, user manuals, etc | 4 days
| 5.2 Project Review & Summary | Review the project and summarize the experiences and lessons learned. | 2 days